## v1.0
Version | Task | Category | Description | Status | Started On | Completed On | Notes
| refactor view models | shared view models |  | done | 2020-11-23 | 2020-11-28
| refactor framework modules | framework modules | move all 3rd party interfaces/code to framework modules | done | 2020-12-01 | 2020-12-09
| change ui command processing to execute synchronously |  | all ui commands need to be updated to execute synchrously and return any command processing errors | done | 2020-12-13 | 2020-12-27
1.05 | refactor messaging rest client to use httpclient | messaging rest client | move to standardize on .net http client and system.text.json for messaging serialization | done | 2021-01-08 | 2021-02-02 | version - starts with name related to software-dev-plan row id. Master branch will be used for deployment and bug fixes only
1.06 | market data feed stream ovverrun | market data feed | maraket data feed option events are continuing to be processed after market data feed has beed turned off | on hold
1.07 | refactor trade blotter | ui | update trade blotter to use custom controls for diiferent views | done | 2021-03-14 | 2021-03-21
1.08 | refactor ui models | ui | refactor model service calls to use base execute function | done | 2021-03-22 | 2021-03-27
1.09 | refactor command handlers | command aggregates | create separate event handler object for each command |  |  |  | easier to maintain and update without affecting other commands
1.1 | Scheduled Tasks | system | create FuturesMarketClose scheduled tasks | done | 2023-03-12 | 2023-03-12
1.2 | Rsi Signal Service | market data feed | create Rsi Signal service to run every 30 seconds and create rsi signal from latest futures eod data | done | 2023-03-13 | 2023-03-13
1.3 | refactor blackboard service | system | simplify blackboard service based on redis data cache | done | 2023-03-15 | 2023-04-03
1.4 | create server manager | system | create new .Net 7.0 server manager app/ui to start & shutdown system services as well as add ui monitoring as required | new
1.5 | Scheduled Task | system | create Futures Market Open scheduled task | new
1.6 | Option Pricer Server |  | move option pricer server based on CUDA generated MonteCarlo simulatios to .Net 7.0 version | new
1.7 | Market Data Feed server |  | move market data feed to new .Net 7.0 market data feed server | new
1.8 | Refactor UI to .net 7.0 |  | partial of WinForms UI to .Net 7.0
2 | Move data storage to Postgres |  | move read and write model storage to Postgres database running in Docker | new
2.1 | Refactor Event Source Storage Model |  | create event source storage model into Postgress
2.2 | Refactor Read Models |  | refactor read storage models into Progress
3 | Trade Broker |  | create new .Net 7.0 automated trade broker server to automatically trade futures options trades | new
4 | Port Ui to WPF |  | complete redo UI into .Net 8.0 WPF | new

## v1.0 - bug fixes
Bug Id | Description | Version | Status | Started | Completed | Notes